## Rod_Matrix_16pcs
MASTER INSPECTION & ACCEPTANCE MATRIX FOR 16 PISTON RODS Ø180x2574 mm (AISI 431)
CELL LEGEND: 🟢 GREEN = Verified & Accepted by Client ¦ 🟡 YELLOW = Factory Measurement (Unconfirmed) ¦ ⚪ WHITE ('To measure') = Pending ¦ 🔴 RED = Defect / HOLD
IDENTIFICATION |  |  |  | RUNOUT IN CENTERS (LIMIT ≤ 0.150 mm) | [6 empty] | DIMENSIONS & LENGTH (LESS = SCRAP!) | [7 empty] | SEALING GROOVES (VIEW A 2:1) | [9 empty] | LEFT THREAD M170x4-6g |  |  |  | RIGHT THREAD M170x4-6g |  |  |  | CHROME & HARDNESS | [5 empty] | NON-DESTRUCTIVE TESTING |  |  | PHOTO & VIDEO EVIDENCE |  |  | FINAL VERDICT & ACTION
Rod No. | Marking / Stamp | Client Priority | Current Diagnosis | Left End | 1/4 Left (Ring 1) | Middle (Body) | 1/4 Right (Ring 2) | Right End | Max Runout | Runout Status | Total Length L | Main OD Ø180 f7 | Defect: OD at ends? | Step OD Ø179.9 | Seal Neck Ø171.6 | Undercut Ø164.3 | Left Thread Length | Right End Length | Groove 1 Width | Groove 2 Width | Expansion Acceptance | Groove Depth | Groove Bottom ID | Grind to 179.6 mm | Corner Radius R0.3 | Edge Deburring | Bottom Roughness | Neck Roughness | GO Gauge (Left) | NO-GO Gauge (Left) | Thread Turns (Left) | Thread Verification | GO Gauge (Right) | NO-GO Gauge (Right) | Thread Turns (Right) | Thread Verification | Chrome Thickness (µm) | Excess Grinding | End Face Chipping | Hardness (HRC) | Roughness Ra | Steel Grade | NDT Inspection | Visual Chrome Quality | End Chamfers 3x45° | Video of Runout | Macro Photos | QC Inspector | Client Decision | Acceptance Condition | Factory Action Plan | Risk & Technical Notes
1 .. 16 | Stamp ID on end face | 1: Urgent / 2: Queue / 3: Scrap | Status as of 28.09.2026 | Dial Indicator (mm) | Dial Indicator (mm) | Deflection Check (mm) | Dial Indicator (mm) | Dial Indicator (mm) | Limit ≤ 0.150 mm | PASS / SCRAP | 2574 ± 0.7 mm | 179.917 .. 179.957 mm | Undersize on 300mm ends | 179.804 .. 179.850 mm | 171.500 .. 171.600 mm | Reference dimension | 245 mm (Drawing) | 189 mm (Drawing) | 8.6 +0.15 (Factory fact) | 8.6 +0.15 (Factory fact) | Client concession (+0.05) | 4.0 mm (Drawing) | URGENT TO MEASURE! | HOLD: Awaiting seal check | Factory request r=0.5 | Diamond file / paste lap | Rmax 1.5 µm | Ra ≤ 0.32 µm | Smooth full engagement | Stop ≤ 1.5..2 turns! | No burrs or dents | 100% video check | Smooth full engagement | Stop ≤ 1.5..2 turns! | Transition 20°±15' | 100% video check | Spec: 80-100 µm | Cylindrical grinder only | Blend into 3x45° chamfer | Drawing: 50-55 HRC | Spec: Ra ≤ 0.30 µm | AISI 431 (Spectrometer) | No subsurface cracks | No pores, blisters or marks | Both ends per drawing | Continuous from stamp ID | Grooves, threads, chamfers | Responsible person | Pass / Rework / Strict Scrap | Client requirement | Concrete shop floor action | Analysis of rod salvage
Rod #1 | Stamp ID on end | 3: Scrap | Runout 0.170 mm (>0.15), HRC=45.8. Ra=0.093 µm. | To measure | 0.18 | 0.15 | 0.18 | To measure | 0.17 | SCRAP (>0.150 mm) | 2574 | 179.93 | In tolerance per factory report | 179.82 | 171.56 | 164.28 | 245 | 189 | 8.86 | 8.86 | Rejected (rod scrapped) | 4 | Scrapped | Scrapped | Factory asked r=0.5 (Under review) | Scrap | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 45.8 | 0.093 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Video available | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | ❌ STRICT SCRAP | Runout 0.170 mm exceeds agreed 0.15 mm limit! Hardness 45.8 < 50 HRC. | Factory refund / remake batch. Regrinding to 179.65 rejected (Core induction 45.8 < 50 HRC). | Scrap confirmed by runout and low core hardness.
Rod #2 | Stamp ID on end | 1: Urgent Delivery | Ready for acceptance. Check threads with NO-GO gauge. Check Ø180 (fact 179.91 mm). | To measure | To measure | To measure | To measure | To measure | To measure | To measure | 2574 | 179.91 | In tolerance per factory report | 179.825 | 171.55 | 164.3 | 245 | 189 | 8.85 | 8.87 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 49.6 | 0.096 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Record on video | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | 🟢 READY FOR ACCEPTANCE | Acceptable: verify thread with NO-GO gauge, confirm Ø180 with micrometer | 100% video check with NO-GO ring gauge | 1st priority batch for delivery.
Rod #3 | Stamp ID on end | 3: Strict Scrap | Neck Ø171.45 (-0.05 mm under tolerance!), chrome 850 µm, HRC=46.5. | To measure | To measure | To measure | To measure | To measure | To measure | To measure | 2574 | 179.92 | In tolerance per factory report | 179.84 | 171.45 | 164.3 | 245 | 189 | 8.9 | 8.88 | Rejected (rod scrapped) | 4 | Scrapped | Scrapped | Factory asked r=0.5 (Under review) | Scrap | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 850 | 850 µm surge (Scrap) | Blend into smooth chamfer | 46.5 | 0.183 | AISI 431 (Confirmed) | PASSED (No defects) | 850 µm surge | Deburr edges | Record on video | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | ❌ STRICT SCRAP | Client strictly rejects: dimension under drawing, chrome surge 850 µm! | Factory refund / remake from scratch. Brush plating (刷镀) proposal rejected: dynamic delamination risk at 35 MPa. | Undersized neck and 850 µm chrome surge cannot be repaired.
Rod #4 | Stamp ID on end | 1: Urgent (PASS) | Runout 0.040 mm (≤0.15). HRC=51.3. Groove edges polished. | To measure | 0.05 | 0.03 | 0.04 | To measure | 0.04 | PASS (≤0.15 mm) | 2574 | 179.94 | In tolerance per factory report | 179.805 | 171.55 | 164.35 | 245 | 189 | 8.87 | 8.87 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 51.3 | 0.11 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Video available | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | 🟢 READY FOR ACCEPTANCE | Acceptable: confirm thread with NO-GO gauge (stop ≤1.5 turns) | Hand lap groove edges, ship to client | One of best rods! Runout with huge safety margin.
Rod #5 | Stamp ID on end | 1: PASS BY RUNOUT! | Runout 0.073 mm (PASS ≤0.15 mm!). HRC=47.0. | To measure | 0.07 | 0.07 | 0.08 | To measure | 0.073 | PASS (≤0.15 mm) | 2574 | 179.93 | In tolerance per factory report | 179.81 | 171.55 | 164.34 | 245 | 189 | 8.86 | 8.87 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 47 | 0.212 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Video available | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | 🟢 PASS BY RUNOUT | Acceptable: runout 0.073 ≤ 0.15! Confirm thread with NO-GO gauge | Lap groove edges, gauge check | Saved by client concession to 0.15 mm runout!
Rod #6 | Stamp ID on end | 1: Urgent (Thread?) | Runout 0.140 mm (PASS ≤0.15). HRC=51.3. Suspicion of thread undersize! | To measure | 0.15 | 0.15 | 0.12 | To measure | 0.14 | PASS RUNOUT (≤0.15) | 2574 | 179.95 | In tolerance per factory report | 179.82 | 171.58 | 164.34 | 245 | 189 | 8.89 | 8.86 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | Suspected undersize >2 turns | Visually clear | 100% check required | Factory: Pass (合格) | Suspected undersize >2 turns | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 51.3 | 0.135 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Video available | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | ⚠️ CRITICAL THREAD | Client strictly rejects if NO-GO gauge engages >2 turns! | Urgent video test with M170x4-6g NO-GO gauge | Passed runout. Destiny depends 100% on NO-GO thread gauge.
Rod #7 | Stamp ID on end | 2: Rework (Chrome) | Chrome 150 µm (+50 µm excess). Grind 50 µm on cylindrical grinder. | To measure | To measure | To measure | To measure | To measure | To measure | To measure | 2574 | 179.925 | In tolerance per factory report | 179.82 | 171.52 | 164.37 | 245 | 189 | 8.84 | 8.87 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 150 | Machine grind 50 µm | Blend into smooth chamfer | 50.6 | 0.146 | AISI 431 (Confirmed) | PASSED (No defects) | Excess thickness (to grind) | Deburr edges | Record on video | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | 🔄 ACCEPT AFTER GRINDING | Accept ONLY after precision machine grinding 50 µm down to 100 µm! | Machine grinding of 50 µm chrome to 100 µm spec. Finished OD must stay in f7 (179.917–179.957 mm). Grinding to 179.86 is forbidden! | Manual grinding is STRICTLY PROHIBITED to avoid waviness!
Rod #8 | Stamp ID on end | 2: Rework (Chrome) | Chrome 130 µm (+30 µm excess). Grind 30 µm on cylindrical grinder. | To measure | To measure | To measure | To measure | To measure | To measure | To measure | 2574 | 179.92 | In tolerance per factory report | 179.82 | 171.52 | 164.4 | 245 | 189 | 8.87 | 8.87 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 130 | Machine grind 30 µm | Blend into smooth chamfer | 50.3 | 0.14 | AISI 431 (Confirmed) | PASSED (No defects) | Excess thickness (to grind) | Deburr edges | Record on video | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | 🔄 ACCEPT AFTER GRINDING | Accept ONLY after precision machine grinding 30 µm down to 100 µm! | Machine grinding of 30 µm chrome to 100 µm spec. Finished OD must stay in f7 (179.917–179.957 mm). Grinding to 179.86 is forbidden! | Fully acceptable after precision machine re-grinding.
Rod #9 | Stamp ID on end | 1: Urgent (Thread?) | Runout 0.140 mm (PASS ≤0.15). Critical groove width 9.10 mm! | To measure | 0.15 | 0.15 | 0.12 | To measure | 0.14 | PASS RUNOUT (≤0.15) | 2574 | 179.92 | In tolerance per factory report | 179.83 | 171.57 | 164.48 | 245 | 189 | 9.05 | 9.1 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | Suspected undersize >2 turns | Visually clear | 100% check required | Factory: Pass (合格) | Suspected undersize >2 turns | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 48.3 | 0.103 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Video available | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | ⚠️ CRITICAL THREAD / GROOVE | NO-GO gauge must stop ≤2 turns. Confirm 9.10 mm groove acceptance. | Video test of NO-GO gauge and client groove concession | Passed runout (0.140 ≤ 0.15). Check thread.
Rod #10 | Stamp ID on end | 2: Queue (OD ends) | Runout 0.117 mm (≤0.15). FACTORY ADMITTED: ends 300mm have Ø180 undersized to 179.89 mm! | To measure | 0.12 | 0.15 | 0.08 | To measure | 0.117 | PASS RUNOUT (≤0.15) | 2574 | 179.92 (300mm: 179.89) | YES: 179.89 mm on 300mm ends! | 179.84 | 171.53 | 164.2 | 245 | 189 | 8.85 | 8.9 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 49.8 | 0.168 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Video available | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | ⚠️ OD UNDERSIZE AT ENDS | Client rejects dimensions under drawing (179.89 < 179.917). Re-measurement required! | Independent OD micrometer measurement every 100 mm | If 179.89 mm confirmed — scrap under Condition #4.
Rod #11 | Stamp ID on end | 1: PASS BY RUNOUT! | Runout 0.120 mm (PASS ≤0.15 mm!). Chrome 100 µm, HRC=49.1. | To measure | 0.12 | 0.12 | 0.12 | To measure | 0.12 | PASS (≤0.15 mm) | 2574 | 179.94 | In tolerance per factory report | 179.83 | 171.54 | 164.32 | 245 | 189 | 8.87 | 8.85 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 49.1 | 0.098 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Video available | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | 🟢 PASS BY RUNOUT | Acceptable: runout 0.120 ≤ 0.15! Confirm thread with NO-GO gauge | Gauge check, groove edge de-burring | Saved by 0.15 mm runout concession.
Rod #12 | Stamp ID on end | 2: Queue | Pending runout measurement in centers. Step Ø179.80 (4 µm under tolerance). | To measure | To measure | To measure | To measure | To measure | To measure | To measure | 2574 | 179.94 | In tolerance per factory report | 179.8 | 171.53 | 164.3 | 245 | 189 | 8.87 | 8.86 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 48.8 | 0.092 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Record on video | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | ⚪ PENDING MEASUREMENTS | Measure runout in 5 points, confirm thread with NO-GO gauge | Perform dial indicator runout check | 2nd priority queue.
Rod #13 | Stamp ID on end | 2: Queue (Thread) | HRC=52.1 (excellent). Video shows suspected dents on thread. | To measure | To measure | To measure | To measure | To measure | To measure | To measure | 2574 | 179.92 | In tolerance per factory report | 179.86 | 171.5 | 164.35 | 245 | 189 | 8.87 | 8.86 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | Suspected dents | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 52.1 | 0.079 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Record on video | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | ⚠️ RE-CHECK THREAD | Check thread with GO and NO-GO gauges, confirm no dents | Video record of thread engagement M170x4-6g | Metal and hardness good, resolve thread issue.
Rod #14 | Stamp ID on end | 1: PASS BY RUNOUT! | Runout 0.110 mm (PASS ≤0.15 mm!). HRC=49.8. | To measure | 0.11 | 0.12 | 0.1 | To measure | 0.11 | PASS (≤0.15 mm) | 2574 | 179.92 | In tolerance per factory report | 179.86 | 171.53 | 164.4 | 245 | 189 | 8.87 | 8.84 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 49.8 | 0.28 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Video available | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | 🟢 PASS BY RUNOUT | Acceptable: runout 0.110 ≤ 0.15! Confirm thread with NO-GO gauge | Lap groove edges, thread verification | Saved by 0.15 mm runout concession.
Rod #15 | Stamp ID on end | 3: Strict Scrap | Step Ø179.55 (-0.25 mm under drawing!), neck Ø171.40, HRC=45.7. | To measure | To measure | To measure | To measure | To measure | To measure | To measure | 2574 | 179.94 | In tolerance per factory report | 179.55 | 171.4 | 164.3 | 245 | 189 | 8.77 | 8.87 | Rejected (rod scrapped) | 4 | Scrapped | Scrapped | Factory asked r=0.5 (Under review) | Scrap | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 45.7 | 0.11 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Record on video | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | ❌ STRICT SCRAP | Client strictly rejects: severe undersize on seating diameters! | Factory refund / remake batch. Brush plating (刷镀) proposal rejected: -0.25 mm step and 45.7 HRC cannot be repaired. | Cannot be repaired. Shop floor machining scrap.
Rod #16 | Stamp ID on end | 1: Urgent (BENCHMARK) | Runout 0.033 mm (benchmark!). Chrome 100 µm, grooves 8.62 mm. | To measure | 0.02 | 0.03 | 0.05 | To measure | 0.033 | PASS (≤0.15 mm) | 2574 | 179.92 | In tolerance per factory report | 179.85 | 171.5 | 164.4 | 245 | 189 | 8.62 | 8.62 | Accepted by client (+0.05) | 4 | URGENT TO MEASURE | HOLD: Check seals first! | Factory asked r=0.5 (Under review) | Mandatory diamond hand lapping | Rmax 1.5 (In spec) | Ra ≤ 0.32 (In spec) | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Visually clear | 100% check required | Factory: Pass (合格) | To measure (≤1.5..2 turns) | Transition 20°±15' | 100% check required | 100 | Not required (100 µm spec) | Blend into smooth chamfer | 48 | 0.124 | AISI 431 (Confirmed) | PASSED (No defects) | No blisters or pores | Deburr edges | Video available | Macro photo required | Factory: 汪秀玉 (Wang Xiuyu) | 🟢 PASS (BENCHMARK) | Highest delivery priority! Confirm thread with NO-GO gauge | Lap groove edges, prepare for immediate dispatch | Best rod of entire batch, perfect geometry.

## Client_5_Conditions_Guide
GUIDE TO CLIENT 5 ACCEPTANCE & SALVAGE CONDITIONS
Condition # | Technical Criterion | Strictness / Concession | Acceptance & Salvage Regulation
Condition 1 | Runout / Eccentricity | CONCESSION AGREED UP TO 0.150 mm | All rods with runout ≤ 0.150 mm are ACCEPTED. Salvaged: #4 (0.040), #5 (0.073), #6 (0.140), #9 (0.140), #10 (0.117), #11 (0.120), #14 (0.110), #16 (0.033). Rod #1 (0.170 mm) is SCRAPPED.
Condition 2 | Threads M170x4-6g | STRICT SCRAP IF DAMAGED | Inspection with GO and NO-GO thread ring gauges. NO-GO gauge MUST stop within 1.5–2 turns. Formal factory 'Pass' without NO-GO gauge is rejected!
Condition 3 | Chrome Layer Thickness | REWORK BY PRECISION GRINDING (>100 µm) | Rods #7 (150 µm) and #8 (130 µm) accepted ONLY after precision machine grinding (strip 50 µm and 30 µm down to 100 µm). Manual grinding strictly forbidden! Rod #3 with 850 µm surge is scrap.
Condition 4 | Dimensions & Length | STRICT SCRAP IF UNDERSIZED | Dimensions smaller than drawing lower limit = strict scrap. Rods #3 (Ø171.45 < 171.50) and #15 (Ø179.55 < 179.804) scrapped. Rod #10 with 179.89 mm on ends requires re-checking!
Condition 5 | Sealing Grooves & Grinding | PAUSE ON 179.6 mm GRINDING! | STOP GRINDING step to 179.6 mm until factory measures groove bottom internal diameter! Sealing manufacturer needs exact dimensions to calculate custom seals. Hand deburr groove edges with diamond file.

## Final_Sorting_and_Dispatch
FINAL STATUS OF 16 PISTON RODS (BATCH OF 28.09.2026)
Readiness Category | Quantity | Rod Numbers | Mandatory Action Before Shipment
🟢 READY FOR SHIPMENT (Urgent) | 5 pcs | # 4, 5, 11, 14, 16 | Confirm thread with NO-GO gauge (stop ≤1.5..2 turns), measure groove bottom ID, deburr edges with diamond file, ship.
🟢 READY PENDING THREAD/OD | 1 pc | # 2 | Check runout in centers and verify thread with NO-GO gauge. Confirm Ø180 with micrometer.
⚠️ CRITICAL THREAD RE-CHECK | 2 pcs | # 6, # 9 | Runout is PASS (0.140 ≤ 0.15). Crucial factor is NO-GO gauge M170x4-6g. On #9 confirm groove width 9.10 mm.
🔄 REWORK: CHROME GRINDING | 2 pcs | # 7, # 8 | Precision machine grinding: strip 50 µm (#7) and 30 µm (#8) to 100 µm spec. Manual grinding STRICTLY FORBIDDEN.
⚠️ SUSPECTED UNDERSIZED OD | 1 pc | # 10 | Runout 0.117 is PASS. Factory admitted 179.89 mm on 300mm ends. Re-measure with micrometer!
⚪ PENDING RUNOUT CHECK | 2 pcs | # 12, # 13 | Measure runout in centers at 5 points, test thread with NO-GO gauge, measure groove bottom ID.
❌ CONFIRMED SCRAP | 3 pcs | # 1, # 3, # 15 | #1: Runout 0.170 > 0.15 & HRC 45.8. #3: Ø171.45 under tolerance & chrome 850 µm surge. #15: Step Ø179.55 (-0.25 mm). Refund / remake.